## Gantt Chart - Manual End Date
Gantt Chart - Thesis Wake Superposition - Ottelien Bossuyt
| Task Name | Start Date | End Date | Duration (Days) | Days Complete | Days Remaining | Percent Complete | Start Date in Number Form | 43040 | Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
| Deadlines | 2017-11-01 |  |  |  |  | 0%
1 | Literature Study | 2017-11-01 | 2018-01-15 | 75 | 75 | 0 | 100%
1.1 | Reading | 2017-11-01 | 2017-12-15 | 44 | 44 | 0 | 100%
1.2 | Writing | 2017-12-10 | 2018-01-15 | 36 | 36 | 0 | 100%
0 | Exams | 2017-12-11 | 2017-12-22 | 11 | 11 | 0 | 100%
0 | Holidays | 2017-12-23 | 2018-01-03 | 11 | 11 | 0 | 100%
2 | Implementing Wake Models | 2018-01-15 | 2018-02-15 | 31 | 9.3 | 21.7 | 30%
2.1 | Model 1: Park | 2018-01-19 | 2018-01-26 | 7 | 7 | 0 | 100%
2.2 | Model 2: Bastankhah | 2018-02-02 | 2018-02-07 | 5 | 0 | 5 | 0%
2.3 | Model 3: Larsen | 2018-02-11 | 2018-02-15 | 4 | 0 | 4 | 0%
2.4 | Model 4: Fuga | 2018-02-05 | 2018-02-06 | 1 | 1 | 0 | 100%
3 | Research Methodologies | 2018-01-23 | 2018-01-26 | 3 | 3 | 0 | 100%
4 | Data readout | 2018-01-27 | 2018-02-15 | 19 | 0 | 19 | 0%
4.1 | BEACon | 2018-01-27 | 2018-01-31 | 4 | 1.2 | 2.8 | 30%
4.2 | LES | 2018-02-07 | 2018-02-10 | 3 | 0.15 | 2.85 | 5%
5 | Validation | 2018-02-16 | 2018-04-30 | 73 | 0 | 73 | 0%
5.1 | Wake recovery | 2018-02-16 | 2018-03-02 | 14 | 0 | 14 | 0%
5.2 | Wake close to rated WS | 2018-03-06 | 2018-03-20 | 14 | 0 | 14 | 0%
5.3 | Wake change upstream | 2018-03-21 | 2018-04-04 | 14 | 0 | 14 | 0%
| Wake expansion rate | 2018-04-04 | 2018-04-23 | 19 | 0 | 19 | 0%
5.4 | Extra topic/buffer | 2018-04-16 | 2018-04-29 | 13 | 0 | 13 | 0%
| Writing | 2018-03-01 | 2018-06-29 | 120 | 0 | 120 | 0%
| Draft writing | 2018-03-01 | 2018-04-30 | 60 | 0 | 60 | 0%
| Final writing | 2018-04-30 | 2018-06-15 | 46 | 0 | 46 | 0%
| Revision | 2018-06-22 | 2018-06-30 | 8 | 0 | 8 | 0%
| Graduation | 2018-07-01 | 2018-07-15 | 14 | 0 | 14 | 0%